## Project Dashboard
Aircraft Return-to-Service Project
Illustrative Flowshua portfolio example. Fictional, illustrative, and unclassified sample. Not technical instructions, Government work product, federal contract past performance, maintenance release, airworthiness approval, technical authority, or Government acceptance.
Overall Progress |  | Schedule Health |  | Spent / Committed |  | Open RAIDD Items |  | Planned Return Window |  | Project-Control Gates Complete
42.1% |  | At Risk |  | 42% |  | 8 |  | Week 12 |  | 1 of 7
Based on the work completed so far |  | Shows whether the schedule needs attention |  | Spent or committed so far |  | Open risks, assumptions, issues, decisions, and dependencies |  | Planned sample closeout window from the schedule |  | Project-control gates completed before sample closeout
Project Goal | [5 empty] | Project Boundaries
Get one fictional aircraft back to mission-capable status in 12 weeks while keeping the work, parts, inspections, labor, risks, and closeout organized. | [5 empty] | Everything in this workbook is fictional. It is based on general maintenance coordination experience, but it does not include real aircraft data, maintenance instructions, procedures, or operational information.
What Needs Attention | [5 empty] | Project Path
Focus | What We See | Owner | Why It Matters | Next Step | Status | Project Step | Planned Window | Current Forecast | Depends On | Status | What We're Doing
Scope | The main work packages and release checks are set | Project Manager | Keeps extra work from getting added without a decision | Keep change requests controlled | Complete | Initial assessment and plan | Weeks 1-2 | Weeks 1-2 | Condition assessment | Complete | Scope is set and the work plan is in place
Parts | Two key parts still need close follow-up | Procurement Lead | Could affect integration and sample closeout | Keep pressure on the alternate source and delivery date | At Risk | Parts and sequencing | Weeks 2-4 | Weeks 2-4 | Parts list and sourcing | At Risk | Stay on top of long-lead parts
Critical path | The maintenance and quality assurance checks are tied together | Work Center Lead and QA | This drives the return date | Protect shop time and inspection windows | In Progress | Maintenance work | Weeks 4-8 | Weeks 4-8 | Shop time and work-package handoffs | In Progress | Protect the main work windows
Quality | Maintenance checks are being planned before the work ends | Quality Assurance Lead | Helps avoid last-minute rework | Hold time for inspections and evidence review | In Progress | Integration and quality | Weeks 7-10 | Weeks 8-10 | Part arrivals and quality checks | Watch | Stage project evidence before integration is finished
Closeout | Lessons and final paperwork are starting early | Project Manager | Makes the project easier to wrap up cleanly | Start the closeout package | Not Started | Final readiness and closeout | Weeks 10-12 | Weeks 11-12 | Quality release and sponsor approval | Not Started | Keep the final closeout window protected
Work Package Status |  |  |  | What Each Tab Shows
Status | Count |  |  | Tab | What It Shows
Complete | 4 |  |  | Project Charter | Why the project exists, what is included, and who owns what
In Progress | 2 |  |  | Work Packages | The main work, who owns it, progress, and what it depends on
At Risk | 2 |  |  | Master Schedule | The 12-week plan and the parts of the project that drive the final date
Not Started | 7 |  |  | Budget & Forecast | Planned cost, current spend, expected total, and money left
|  |  |  | Procurement & Dependencies | Parts, outside support, delivery dates, and linked work packages
Budget Snapshot |  |  |  | Quality Gates | Project-control gates required before sample closeout
Metric | Value |  |  | RAIDD | Risks, assumptions, issues, decisions, and dependencies
Planned Budget | 600000 |  |  | Lessons Learned | What worked, what did not, and what to use next time
Spent / Committed | 252000 |  |  | Project Dashboard | Quick view of progress, schedule, budget, risk, and readiness
Expected Total Cost | 585000
Budget Remaining | 15000
Flowshua Projects ¦ Clearer workflows. Stronger execution.

## Project Charter
Project Charter
Aircraft Return-to-Service Project. Fictional, illustrative, and unclassified sample. Not technical instructions, Government work product, federal contract past performance, maintenance release, airworthiness approval, technical authority, or Government acceptance.
Project Overview
Project Name | Aircraft Return-to-Service Project |  | Goal | Coordinate a fictional aircraft return-to-service project over 12 weeks while keeping work, generic needs, labor, reviews, and handoffs organized.
Project Type | Fictional aircraft recovery project |  | Why It Matters | Demonstrate how a fictional recovery target can be coordinated while giving leadership a clear view of progress and decisions.
Project Sponsor | Operations Sponsor (fictional role) |  | Main Constraint | Parts availability and the timing of quality checks are what drive the schedule.
Project Manager | Project Manager (portfolio example) |  | Working Assumption | The sample remains outside operational scheduling until illustrative project-control closeout conditions are met.
Planned Length | 12 weeks |  | Success Looks Like | The sample reaches project-control closeout by Week 12, stays within the approved budget, completes all required gates, and documents and closes any resulting rework.
Planned Budget | $600,000 |  | What Is Fictional | All aircraft, dates, costs, parts, and details here are made up for this portfolio example.
Target Outcome | Illustrative Return-to-Service Target |  | How the Project Is Run | Keep ownership clear, raise problems early, and keep the project easy to follow.
What Is Included |  |  |  |  | What Is Not Included
Included | Initial assessment and work planning |  |  |  | Not included | Technical repair instructions or maintenance procedures
Included | Fictional parts planning, tracking, and recovery sequencing |  |  |  | Not included | Real aircraft, unit, system, inspection, or parts information
Included | Work-center coordination, project-control gate reviews, and illustrative closeout |  |  |  | Not included | Operational flight schedules or mission details
Included | Project budget, schedule, risk tracking, and lessons learned |  |  |  | Not included | Real vendor, contract, or supply-chain information
Included | Weekly updates so leadership can see the full picture |  |  |  | Not included | Any claim that this is real Government work product
Who Is Involved and How It Works
Role | What They Care About | What They Decide | How Often | What They Bring | Role | What They Care About | What They Decide | How Often | What They Bring
Operations Sponsor | Reaching the fictional project target | Approves fictional project scope and closeout | Weekly gate review | Priority and sample closeout criteria | Project Manager | Keeping the whole plan together | Coordinates changes and escalations | Daily control review | Clear view of scope, cost, schedule, and risk
Work Center Lead | Work order and team capacity | Sets shop capacity | Daily work review | Progress and resource limits | Procurement Lead | Parts and outside support | Raises long-lead part problems | Twice-weekly parts review | Delivery dates and sourcing confidence
Quality Lead | Project review and readiness tracking | Reviews project-control gate evidence | At each gate | Review timing and project evidence needs | Technical Lead | Work-package coordination | Updates completion forecast | Daily recovery update | Work sequence and technical handoffs
Support / Vendor Lead | Outside support and part delivery | Gives delivery forecast | As needed | Support availability and arrival dates | Project Controls | Cost, schedule, and open items | Keeps the tracker current | Weekly management review | Forecasts, variances, and open-item status
Portfolio Viewer | Understanding the project example | No decision authority | As needed | Uses the workbook to see the approach | Project Boundary | Fictional portfolio project | No outside authority | Always visible | Only made-up, non-sensitive project data
Flowshua Projects ¦ Clearer workflows. Stronger execution.

## Work Packages
Work Package Tracker
Sample work plan, ownership, progress, and dependencies. Fictional, illustrative, and unclassified sample. Not technical instructions, Government work product, federal contract past performance, maintenance release, airworthiness approval, technical authority, or Government acceptance.
Package ID | Phase | Work | Owner | Days | Start Week | Finish Week | Weight | Status | % Complete | Earned % | Depends On | Schedule Effect | Notes
WP-001 | Initiation | Check aircraft condition and document findings | Technical Lead | 5 | 1 | 1 | 5% | Complete | 100% | 5% | Project kickoff | Low | Findings are captured and the baseline is ready
WP-002 | Initiation | Approve the project plan and illustrative target | Operations Sponsor | 3 | 1 | 1 | 5% | Complete | 100% | 5% | WP-001 | Low | Project goals and closeout target are set
WP-003 | Planning | Build the detailed work plan | Project Manager | 5 | 1 | 2 | 7% | Complete | 100% | 7% | WP-001 | Low | The work is laid out before execution starts
WP-004 | Planning | Confirm parts needed and the sourcing plan | Procurement Lead | 7 | 2 | 3 | 8% | At Risk | 85% | 6.8% | WP-003 | Medium | Two key parts need daily follow-up
WP-005 | Planning | Set the recovery sequence and shop plan | Work Center Lead | 6 | 2 | 3 | 8% | Complete | 100% | 8% | WP-003 | Low | Shop windows and handoffs are clear
WP-006 | Execution | Finish major work package A | Work Center Lead | 20 | 4 | 7 | 10% | In Progress | 60% | 6% | WP-005 | Medium | Protect the work window and keep the package moving
WP-007 | Execution | Finish major work package B | Technical Lead | 20 | 4 | 8 | 10% | At Risk | 35% | 3.5% | WP-004 | High | Part availability is driving the current forecast
WP-008 | Execution | Restore support systems and records | Work Center Lead | 16 | 5 | 8 | 8% | In Progress | 10% | 0.8% | WP-006 | Medium | Keep the records moving with the work
WP-009 | Integration | Install recovered components | Technical Lead | 15 | 7 | 9 | 10% | Not Started | 0% | 0% | WP-007 | High | Do not start until the critical component is in hand
WP-010 | Integration | Run integration checks | Technical Lead | 10 | 8 | 9 | 8% | Not Started | 0% | 0% | WP-009 | High | The configuration needs to be stable first
WP-011 | Quality | Complete the quality review | Quality Lead | 8 | 9 | 10 | 7% | Not Started | 0% | 0% | WP-008 | High | Hold inspection time before the work is done
WP-012 | Quality | Close out any quality fixes | Work Center Lead | 7 | 9 | 10 | 5% | Not Started | 0% | 0% | WP-011 | Medium | Document and close fixes as they are completed
WP-013 | Readiness | Run final readiness checks | Quality Lead | 6 | 10 | 11 | 4% | Not Started | 0% | 0% | WP-012 | High | This must be done before sample closeout
WP-014 | Readiness | Build the sample closeout package | Project Manager | 5 | 11 | 12 | 3% | Not Started | 0% | 0% | WP-013 | High | Line up project evidence, reviews, and final sample records
WP-015 | Closeout | Close the illustrative project and capture lessons learned | Operations Sponsor | 4 | 12 | 12 | 2% | Not Started | 0% | 0% | WP-014 | High | Illustrative project closeout
Flowshua Projects ¦ Clearer workflows. Stronger execution.

## Master Schedule
Master Schedule & Recovery Plan
Sample 12-week project-control plan. Fictional, illustrative, and unclassified sample. Not technical instructions, Government work product, federal contract past performance, maintenance release, airworthiness approval, technical authority, or Government acceptance.
Phase | Main Step | Owner | Start Week | Finish Week | Days | Health | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Initiation | Finish condition assessment | Technical Lead | 1 | 1 | 5 | Complete | ●
Initiation | Approve project charter | Operations Sponsor | 1 | 1 | 3 | Complete | ●
Planning | Finish the detailed work plan | Project Manager | 1 | 2 | 5 | Complete | ● | ●
Planning | Confirm critical parts plan | Procurement Lead | 2 | 3 | 7 | At Risk |  | ● | ●
Planning | Confirm shop capacity and work order | Work Center Lead | 2 | 3 | 6 | Complete |  | ● | ●
Execution | Finish major work package A | Work Center Lead | 4 | 7 | 20 | In Progress |  |  |  | ● | ● | ● | ●
Execution | Finish major work package B | Technical Lead | 4 | 8 | 20 | At Risk |  |  |  | ● | ● | ● | ● | ●
Execution | Restore support systems and records | Work Center Lead | 5 | 8 | 16 | In Progress |  |  |  |  | ● | ● | ● | ●
Integration | Install recovered components | Technical Lead | 7 | 9 | 15 | Not Started | [6 empty] | ● | ● | ●
Integration | Finish integration checks | Technical Lead | 8 | 9 | 10 | Not Started | [7 empty] | ● | ●
Quality | Complete quality review | Quality Lead | 9 | 10 | 8 | Not Started | [8 empty] | ● | ●
Quality | Close out quality fixes | Work Center Lead | 9 | 10 | 7 | Not Started | [8 empty] | ● | ●
Readiness | Run final readiness checks | Quality Lead | 10 | 11 | 6 | Not Started | [9 empty] | ● | ●
Readiness | Prepare sample closeout package | Project Manager | 11 | 12 | 5 | Not Started | [10 empty] | ● | ●
Closeout | Illustrative project closeout and lessons learned | Operations Sponsor | 12 | 12 | 4 | Not Started | [11 empty] | ●
Flowshua Projects ¦ Clearer workflows. Stronger execution.

## Budget & Forecast
Project Budget & Forecast
Sample budget and forecast using fictional amounts. Fictional, illustrative, and unclassified sample. Not technical instructions, Government work product, federal contract past performance, maintenance release, airworthiness approval, technical authority, or Government acceptance.
Planned Budget |  | Spent / Committed |  | Expected Total Cost |  | Budget Remaining | Budget Health
600000 |  | 252000 |  | 585000 |  | 15000 | Watch
Approved project budget |  | Money spent or already committed |  | What the project is expected to cost |  | Forecast headroom remaining in the approved budget | How the forecast compares to the plan
Category | Planned Budget | Spent / Committed | Expected Total | Budget Remaining | Status
Labor and shop support | 155000 | 78500 | 150000 | 5000 | In Progress
Parts and repairable components | 230000 | 102000 | 228000 | 2000 | At Risk
Materials and supplies | 48000 | 23400 | 46500 | 1500 | In Progress
Outside support and vendor help | 72000 | 24000 | 71000 | 1000 | In Progress
Testing and quality | 35000 | 10000 | 33500 | 1500 | Not Started
Contingency | 60000 | 14100 | 56000 | 4000 | On Track
Total | 600000 | 252000 | 585000 | 15000
Flowshua Projects ¦ Clearer workflows. Stronger execution.

## Procurement & Dependencies
Parts & Dependency Tracker
Sample parts, outside-support, and dependency controls using generic fictional needs. Fictional, illustrative, and unclassified sample. Not technical instructions, Government work product, federal contract past performance, maintenance release, airworthiness approval, technical authority, or Government acceptance.
Request | Part / Need | Category | Source | Criticality | Request Week | Expected Arrival | Linked Package | Schedule Effect | Owner | Next Step | Status
PR-001 | Inspection supplies | Quality support | Internal stock | Low | Week 1 | Available now | WP-011 | Low | Quality Lead | Make sure supplies are staged before review | Available
PR-002 | Electrical component | Component | Approved supplier | High | Week 1 | Week 3 | WP-007 | High | Procurement Lead | Check the committed delivery date twice a week | In Review
PR-003 | Mechanical assembly | Component | Approved supplier | Critical | Week 1 | Waiting on forecast | WP-007 | Critical | Procurement Lead | Work the alternate source and expedited shipping | At Risk
PR-004 | Seal and hardware kit | Materials | Internal stock | Medium | Week 2 | Week 2 | WP-006 | Medium | Work Center Lead | Check that the kit is complete before work starts | Available
PR-005 | Support equipment fixture | Support equipment | Shared pool | Medium | Week 4 | Week 4 | WP-009 | Medium | Technical Lead | Reserve the fixture for the integration window | Confirmed
PR-006 | Vendor diagnostic support | Outside support | Service partner | High | Week 6 | Week 8 | WP-010 | High | Procurement Lead | Lock in the support date before checks start | In Review
PR-007 | Verification materials | Quality support | Internal stock | Low | Week 8 | Week 8 | WP-011 | Low | Quality Lead | Stage the materials before quality review | Available
PR-008 | Closeout paperwork | Documentation | Project controls | Medium | Week 10 | Week 11 | WP-014 | Medium | Project Manager | Start pulling the records together before sample closeout | Not Started
Flowshua Projects ¦ Clearer workflows. Stronger execution.

## Quality Gates
Project-Control Gates & Closeout Checklist
Illustrative project-control readiness gates only. Fictional, illustrative, and unclassified sample. Not technical instructions, Government work product, federal contract past performance, maintenance release, airworthiness approval, technical authority, or Government acceptance.
Gate | Phase | Check / Decision | What We Need | Owner | Week | Status | Schedule Effect | Next Step | Ready When
G-001 | Planning | Approve the project scope | Charter, work package list, and starting risk log | Operations Sponsor | 2 | Complete | Low | Keep change requests controlled | The project goal and work list are approved
G-002 | Planning | Confirm the parts plan | Parts list, sourcing plan, and delivery dates | Procurement Lead | 3 | At Risk | High | Work the alternate source for critical parts | Critical parts have a solid arrival forecast
G-003 | Execution | Finish major work package A | Completed package record and quality evidence | Work Center Lead | 7 | In Progress | Medium | Protect the work window and handoffs | The package is done and the handoff is documented
G-004 | Execution | Finish major work package B | Completed package record and part availability confirmation | Technical Lead | 8 | At Risk | High | Review part ETA and schedule every day | The critical work is done inside the recovery window
G-005 | Integration | Verify component integration | Integration checklist and fit confirmation | Technical Lead | 9 | Not Started | High | Hold support and check time | The configuration is stable for quality review
G-006 | Quality | Finish the quality review | Quality package and closed corrective actions | Quality Lead | 10 | Not Started | High | Stage evidence and inspection time early | No open project-review action blocks sample closeout
G-007 | Readiness | Complete illustrative project-control closeout | Readiness summary, fictional sponsor closure, and closeout record | Operations Sponsor | 12 | Not Started | Critical | Set the final review meeting and sample closeout package | Fictional sponsor closes the illustrative project-control record
Flowshua Projects ¦ Clearer workflows. Stronger execution.

## RAIDD
RAIDD Log
Sample risks, assumptions, issues, decisions, and dependencies. Fictional, illustrative, and unclassified sample. Not technical instructions, Government work product, federal contract past performance, maintenance release, airworthiness approval, technical authority, or Government acceptance.
ID | Type | What Could Happen / What We Know | Owner | Impact | Priority | Due Week | Status | Next Step
R-01 | Risk | A critical part could miss the integration window | Procurement Lead | Could delay major work package B and integration | Critical | Week 3 | Open | Confirm the alternate source and update delivery confidence
R-02 | Risk | A new condition found during work could add more scope | Technical Lead | Could need a scope decision and use some contingency | High | Week 6 | Open | Review scope before any extra work is approved
R-03 | Risk | Quality review time may not line up with recovery completion | Quality Lead | Could delay the project closeout review after work is done | High | Week 9 | Open | Hold the review window and stage evidence early
A-01 | Assumption | The planned budget has enough contingency for small changes | Project Manager | The budget stays on track if changes stay within reserve | Medium | Week 4 | Open | Review contingency use in the weekly cost check
A-02 | Assumption | The shop has the people and time needed for the main work windows | Work Center Lead | A resource conflict could slow down the recovery plan | High | Week 5 | Open | Confirm capacity before each weekly schedule lock
I-01 | Issue | The critical part delivery date is still uncertain | Procurement Lead | The integration start date is exposed | Critical | Week 3 | At Risk | Escalate sourcing options and get firmer delivery dates
I-02 | Issue | Major work package B is moving slower than planned | Technical Lead | Could squeeze the quality and readiness window | High | Week 8 | Open | Shift labor where needed and protect completion checks
D-01 | Decision | Use a full project-control closeout gate instead of partial closeout | Operations Sponsor | Keeps project review and readiness decisions clear | High | Week 2 | Approved | Keep all illustrative gates before sample closeout
D-02 | Decision | Hold contingency until the critical part forecast is clearer | Project Manager | Prevents the budget from being used too early | High | Week 3 | Approved | Only use reserve through a change review
D-03 | Dependency | Sample closeout depends on project review, readiness tracking, and fictional sponsor closure | Quality Lead | This sets the final Week 12 sample closeout condition | Critical | Week 12 | Open | Track these items as one linked closeout gate
Flowshua Projects ¦ Clearer workflows. Stronger execution.

## Lessons Learned
Closeout & Lessons Learned
Sample closeout and reuse controls. Fictional, illustrative, and unclassified sample. Not technical instructions, Government work product, federal contract past performance, maintenance release, airworthiness approval, technical authority, or Government acceptance.
What We Have Learned So Far
Lesson ID | Project Moment | What Happened | What We Learned | What To Do Next Time | Owner | Where It Helps | Status
LL-01 | Scope baseline | The early assessment stopped extra work from slipping into the active plan without a review. | Set the scope early, then make changes visible before adding work. | Keep a simple baseline and change log before major work starts. | Project Manager | Future recovery projects | Complete
LL-02 | Parts planning | One long-lead part created a lot of schedule pressure. | Start critical parts work early and always look at a backup source. | Flag critical parts and check delivery confidence twice a week. | Procurement Lead | Parts and dependency tracking | In Progress
LL-03 | Shop capacity | Too much work hit the most limited recovery package at the same time. | Protect critical-path work before lower-priority tasks. | Lock in shop time each week for the work that drives the date. | Work Center Lead | Resource planning | In Progress
LL-04 | Quality planning | Waiting too long to plan verification would have squeezed the release window. | Build evidence and inspection needs into the work package from the start. | Stage quality evidence before the work is finished. | Quality Lead | Quality-gate checklist | Not Started
LL-05 | Leadership visibility | A simple weekly dashboard made it easier to raise problems early. | Leaders need a quick view of scope, cost, schedule, risk, and readiness. | Use the same dashboard format during active recovery work. | Project Manager | Project control dashboard | Complete
Closeout Checklist
Closeout Item | Owner | Target Week | What We Need | Status | Why It Matters | Follow-up | Portfolio Note
Sample closeout package | Project Manager | Week 12 | Project reviews, closeout record, and final sample summary | Not Started | Shows the illustrative project-control record is complete | Prepare it before the final project review | Fictional portfolio example
Budget wrap-up | Project Controls | Week 12 | Final forecast, variance notes, and contingency use | Not Started | Shows how the project finished against the plan | Update it as final vendor costs become clear | Sample cost-control view
RAIDD review | Project Manager | Week 12 | Final status of open items and decisions | Not Started | Makes sure nothing gets lost at closeout | Close or hand off every open item | Sample project control
Lessons learned review | Operations Sponsor | Week 12 | Final lessons summary and repeatable standards | Not Started | Turns the project into something useful next time | Review it with the recovery leads | Public, portfolio-safe summary
Workbook archive | Project Manager | Week 12 | Final workbook and project summary | Not Started | Keeps the project easy to explain and reuse | Publish the approved portfolio version | No real operational data included
Flowshua Projects ¦ Clearer workflows. Stronger execution.

## Flowshua Brand Palette
Flowshua Brand Palette
Reference palette for this fictional public sample. Fictional, illustrative, and unclassified sample. Not technical instructions, Government work product, federal contract past performance, maintenance release, airworthiness approval, technical authority, or Government acceptance.
Brand Element | Hex | Use It For | Preview
Primary navy | #102A43 | Titles, main headers, and footers
Secondary navy | #173F5F | Section bars and page structure
Flowshua orange | #F47C20 | Accent strips, actions, and emphasis
Warm ivory | #F8F5EF | Light content areas and visual breathing room
White | #FFFFFF | High-contrast text and clean content cards
Border gray | #D9E1E7 | Light framing and separation
Muted slate | #5E6C78 | Subtitles, labels, and secondary text
Status | Fill | Text | Use It For
On track / complete | #DDE8DF | #3F6248 | Finished work, approved checks, and completed decisions
In progress / watch | #F5E4BF | #7B571B | Active work and items that need attention
At risk / critical | #F0D6D1 | #7B4038 | Schedule, cost, or dependency problems
Not started / review | #E9EDF0 | #59636D | Planned work or items waiting for confirmation
Use navy for structure, orange for deliberate emphasis, ivory for readability, and status colors only when they communicate project condition.
Flowshua Projects ¦ Clearer workflows. Stronger execution.

## Start Here
Aircraft Return-to-Service Project Controls Workbook
Public sample workbook navigation. Fictional, illustrative, and unclassified sample. Not technical instructions, Government work product, federal contract past performance, maintenance release, airworthiness approval, technical authority, or Government acceptance.
Purpose and Responsible Use
This workbook demonstrates how Flowshua can structure an aircraft return-to-service project using scope, schedule, cost, procurement, quality, RAIDD, and closeout controls. All aircraft, dates, costs, parts, organizations, and project details are fictional. This is not a maintenance procedure, official government form, technical instruction, or federal contract past-performance claim.
Workbook Navigation
Tab | Purpose | Primary Inputs | Key Outputs
Project Dashboard | Leadership snapshot | Supporting tabs | Progress, health, open items, budget, and readiness
Project Charter | Purpose, scope, roles, and boundaries | Project assumptions | Approved project-control framework
Work Packages | Work breakdown and ownership | Status and percent complete | Weighted progress and dependencies
Master Schedule | 12-week recovery plan | Start and finish weeks | Timeline and schedule health
Budget & Forecast | Cost plan and forecast | Planned, committed, and expected cost | Forecast variance and budget remaining
Procurement & Dependencies | Parts and external support tracking | Arrival forecast and status | Schedule exposure and next steps
Quality Gates | Project-control closeout gates | Gate status and evidence needs | Readiness and closeout visibility
RAIDD | Risk and decision control | Owner, priority, due week, status | Management attention and follow-through
Lessons Learned | Closeout and reuse | Observed outcomes and actions | Repeatable practices and closeout checklist
How to Use the Sample
1 | Review the Project Dashboard for the current management picture
2 | Update status, percent complete, costs, arrivals, and RAIDD records in the working tabs
3 | Use the schedule, budget, and gate views to identify forecast exposure
4 | Use the dashboard and lessons-learned views for leadership reporting and closeout
5 | Replace all fictional data before adapting this structure for an authorized client engagement