## Executive Dashboard
FLOWSHUA PROJECTS LLC ¦ PROGRAM SUPPORT CONTROL WORKBOOK
Illustrative work sample ¦ Fictional, unclassified program office scenario ¦ Not an official U.S. Government form
Program: | Program Meridian (fictional illustrative program) |  | Data Date: | 2026-07-18 | Overall Status: | Amber
Open Actions | Overdue Actions | Open RAID Items | High Impact RAID | Pending Decisions | Open Deliverables | Deliverables Due <7 Days | Docs Pending Review
4 | 2 | 4 | 2 | 2 | 3 | 2 | 1
PROGRAM SUPPORT SUMMARY
Area | Open Count | Overdue / High Priority | Closed / Resolved (period) | Source Tab
Actions | 4 | 2 | 1 | Action Tracker
Deliverables | 3 | 2 | 0 | Deliverables Register
RAID Items | 4 | 2 | 0 | RAID Log
Decisions | 2 | 0 | 1 | Decision Log
Documents | 1 | 1 | 3 | Document Register

## Operating Rhythm Calendar
OPERATING RHYTHM CALENDAR
Recurring program support battle rhythm ¦ Update Next Occurrence after each event
Event ID | Cadence | Meeting / Event | Owner | Attendees | Typical Output | Next Occurrence | Notes
OR-01 | Daily | Program Support Standup | Program Coordinator | Support Staff | Action status check, blockers surfaced | 2026-07-19 | 15 min, standing
OR-02 | Weekly | Program Status Review | Program Lead | Functional Leads, Coordinator | Weekly Status Report issued | 2026-07-25 | See Reporting Calendar
OR-03 | Weekly | Action & RAID Review | Program Coordinator | Action/RAID Owners | Updated Action Tracker and RAID Log | 2026-07-25
OR-04 | Biweekly | Working-Level Coordination | Program Coordinator | Functional Leads | Cross-functional dependency check | 2026-08-01
OR-05 | Monthly | Leadership / Customer Review | Program Lead | Leadership, Customer POC | Executive Dashboard briefed | 2026-08-17
OR-06 | Monthly | KPI & Performance Review | Program Lead | Program Support Team | KPI Summary reviewed, trends assessed | 2026-08-17
OR-07 | Quarterly | Document Control Audit | Document Control Lead | Program Coordinator | Document Register reconciled | 2026-10-16

## Meeting Register
MEETING REGISTER
Log of program support meetings ¦ Link minutes and actions generated
Meeting ID | Date | Meeting Name | Type | Facilitator | Key Topics | Actions Generated | Minutes Status | Status
MTG-001 | 2026-07-11 | Weekly Program Status Review | Leadership | Program Lead | Schedule variance, material dependency | 3 | Distributed | Held
MTG-002 | 2026-07-16 | Action & RAID Review | Working Group | Program Coordinator | Overdue action follow-up | 2 | Distributed | Held
MTG-003 | 2026-07-23 | Leadership / Customer Review | Customer | Program Lead | Monthly performance summary | 0 | Pending | Scheduled

## Action Tracker
ACTION TRACKER
All open, in-work, and closed program support actions
SUMMARY
[9 empty] | Open (incl. In Work) | 4
[9 empty] | Overdue | 2
[9 empty] | Closed (all time) | 1
Action ID | Description | Owner | Date Opened | Due Date | Priority | Status | Linked Item | Days Overdue | Notes
ACT-001 | Confirm replacement-material verification with supply lead | Supply Lead | 2026-07-08 | 2026-07-16 | High | Open | RAID-01 | 2 | Escalate if unresolved
ACT-002 | Issue engineering disposition for open drawing question | Engineering Lead | 2026-07-10 | 2026-07-17 | High | In Work | RAID-02 | 1 | Review scheduled
ACT-003 | Approve site access roster for onsite support | Site POC | 2026-07-13 | 2026-07-21 | Medium | Open |  | 0
ACT-004 | Update document register after control-plan revision | Document Control Lead | 2026-07-04 | 2026-07-11 | Medium | Closed | DOC-004 | 0 | Closed on schedule
ACT-005 | Validate test-equipment availability for readiness review | Test Lead | 2026-07-15 | 2026-07-24 | Medium | Open |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Days Overdue = IF([Status]="Closed",0,IF([Status]="Cancelled",0,IF(TODAY()>[Due Date],TODAY()-[Due Date],0)))
Days Overdue = IF([Status]="",0,IF([Status]="Closed",0,IF([Status]="Cancelled",0,IF(TODAY()>[Due Date],TODAY()-[Due Date],0))))

## Deliverables Register
DELIVERABLES REGISTER
Tracked program support deliverables and submissions
SUMMARY
[9 empty] | Open (Not Started/In Progress) | 3
[9 empty] | Due within 7 days | 2
[9 empty] | Closed (Accepted, all time) | 0
Deliverable ID | Description | Owner | Type | Due Date | Status | % Complete | Days Until Due | Linked Meeting/Action | Notes
DEL-001 | Weekly Status Report - Period 3 | Program Coordinator | Report | 2026-07-20 | In Progress | 70% | 2 | MTG-001
DEL-002 | Updated Integrated Milestone Schedule | Program Lead | Schedule | 2026-07-23 | In Progress | 50% | 5
DEL-003 | Monthly KPI Summary | Program Coordinator | Report | 2026-07-30 | Not Started | 0% | 12
DEL-004 | Revised Document Register | Document Control Lead | Register | 2026-07-15 | Submitted | 100% | -3 | DOC-004 | Pending acceptance
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Days Until Due = IF([Status]="Accepted",0,IF([Status]="Rejected",0,[Due Date]-TODAY()))
Days Until Due = IF([Status]="",0,IF([Status]="Accepted",0,IF([Status]="Rejected",0,[Due Date]-TODAY())))

## RAID Log
RAID LOG
Risks, Assumptions, Issues, and Dependencies
SUMMARY
[9 empty] | Open | 4
[9 empty] | Open & High Impact | 2
[9 empty] | Closed (all time) | 0
ID | Type | Statement | Owner | Probability | Impact | Response / Mitigation | Status | Date Identified | Date Closed
RAID-01 | Risk | Key material verification may slip beyond the planned window. | Supply Lead | Medium | High | Daily supplier follow-up; pre-stage partial receipts. | Open | 2026-07-06
RAID-02 | Issue | Open engineering question on a control document. | Engineering Lead | N/A | High | Disposition requested; escalate if unresolved by review. | Open | 2026-07-12
RAID-03 | Assumption | Site work area will remain available through the planned window. | Site POC | N/A | Medium | Validate at readiness review. | Monitoring | 2026-07-09
RAID-04 | Dependency | Test equipment reservation depends on completion of a prior activity. | Test Lead | Medium | Medium | Reserve backup equipment. | Open | 2026-07-14

## Decision Log
DECISION LOG
Decisions requested, pending, and resolved
SUMMARY
[8 empty] | Pending | 2
[8 empty] | Approved (period) | 1
[8 empty] | Overdue (past Needed-By) | 0
Decision ID | Decision Required | Decision Authority | Date Needed | Status | Date Decided | Impact if Delayed | Next Step
DEC-01 | Authorize contingency plan if material receipt slips further. | Program Lead | 2026-07-20 | Pending |  | Protects schedule float. | Coordinator to provide impact comparison.
DEC-02 | Approve use of backup test resource if primary unavailable. | Test Authority | 2026-07-22 | Pending |  | Avoids test-window delay. | Test Lead to confirm compatibility.
DEC-03 | Approve revised document register after control-plan update. | Document Control Lead | 2026-07-13 | Approved | 2026-07-14 | Maintains single controlled baseline. | Register updated.

## Document Register
DOCUMENT REGISTER
Controlled program support documents and version history
SUMMARY
[8 empty] | In Review | 1
[8 empty] | Review Past Due | 1
[8 empty] | Approved (current) | 3
Document ID | Title | Version | Owner | Status | Last Updated | Location / Link | Next Review Date
DOC-001 | Program Support Operating Rhythm and SOP Manual | v1.0 | Program Coordinator | Approved | 2026-06-18 | Program Support Library | 2026-12-15
DOC-002 | Integrated Milestone Schedule | v2.3 | Program Lead | Approved | 2026-07-11 | Program Support Library | 2026-08-10
DOC-003 | Weekly Status Report Template | v1.1 | Program Coordinator | Approved | 2026-06-03 | Templates Folder | 2026-11-30
DOC-004 | Program Support Control Plan | v1.2 | Document Control Lead | In Review | 2026-07-16 | Program Support Library | 2026-07-17

## Reporting Calendar
REPORTING CALENDAR
Recurring reporting obligations and due dates
Report | Frequency | Due Day / Date | Owner | Distribution | Last Submitted | Next Due | Status
Weekly Status Report | Weekly | Every Friday | Program Coordinator | Program Lead, Leadership | 2026-07-11 | 2026-07-18 | On Track
Monthly KPI Summary | Monthly | Last business day | Program Coordinator | Program Lead, Customer | 2026-06-23 | 2026-07-23 | On Track
Executive Dashboard Briefing | Monthly | First review of month | Program Lead | Leadership | 2026-06-20 | 2026-07-20 | On Track
Document Control Audit Summary | Quarterly | End of quarter | Document Control Lead | Program Lead | 2026-04-29 | 2026-07-28 | On Track

## KPI Summary
KPI SUMMARY
Program support performance measures ¦ Reviewed monthly
Metric | Formula / Source | Target | Current | Status | Data Source | Trend Notes
Action Closure Rate | Closed actions / total logged actions | 85% | 20% | Red | Calculated
Overdue Action Rate | Overdue actions / open actions | 10% | 50% | Red | Calculated
Deliverable On-Time Rate | Accepted on/before due date / total closed deliverables | 90% | 92% | Manual Input Required | Manual Input Required
Open High-Impact RAID Items | Count of open Risk/Issue items rated High impact | 0 | 2 | Amber | Calculated
Decision Cycle Time (avg days) | Average days from decision requested to decided | 5 | 4.2 | Manual Input Required | Manual Input Required
Document Currency Rate | Approved documents / total controlled documents | 90% | 75% | Amber | Calculated
Meeting On-Time Rate | Meetings held as scheduled / total scheduled | 90% | 88% | Manual Input Required | Manual Input Required
Note: rows marked "Manual Input Required" have no direct workbook data source. The Current value shown is an illustrative placeholder and must be replaced with an actual measured value before this workbook is used for real reporting.

## Lists (hidden)
Priority | ActionStatus | YesNoNA | RAIDType | ProbImpact | RAIDStatus | DecisionStatus | DocStatus | DeliverableStatus | MeetingType | MeetingStatus | Cadence | OverallStatus | ReportStatus | KPIStatus
High | Open | Yes | Risk | Low | Open | Pending | Draft | Not Started | Standup | Scheduled | Daily | Green | On Track | Green
Medium | In Work | No | Issue | Medium | Monitoring | Approved | In Review | In Progress | Working Group | Held | Weekly | Amber | At Risk | Amber
Low | Closed | N/A | Assumption | High | Closed | Denied | Approved | Submitted | Program Review | Cancelled | Biweekly | Red | Late | Red
| Cancelled |  | Dependency | N/A |  | Deferred | Superseded | Accepted | Leadership | Rescheduled | Monthly | Blue | Submitted
[8 empty] | Rejected | Customer |  | Quarterly
[9 empty] | Ad Hoc |  | Ad Hoc